## excel (2)
/Proyecto/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Program Size
| Plan | Actual | A la Fecha
Base (B) | 533 | 533 | 1900
Deleted (D) | 14 | 7 | 302
Modified (M) | 192 | 49 | 233
Added (A) | 617 | 923 | 3326
Reused (R) | 508 | 508 | 939
Added and Modified (A+M) | 809 | 972 | 3559
Total Size (T) | 1644 | 1957 | 5863
Total New Reusable | 0 | 0 | 11
Estimated Proxy Size (E) | 665 | 965 | 3864
Upper Prediction Interval (70%) | 989
Lower Prediction Interval (70%) | 628
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 15:02 el 30-abr-2017